## Gantt Chart Template Gratis
Project Information:
Project Name: [Project Name]
Start Date: [YYYY-MM-DD]
Overall Progress (%): (Formula-driven - see below)
Task ID | Task Name | Start Date | End Date | Assignee | Duration (Days) | % Complete | Status | Dependencies | Notes
1 | Requirements Gathering | 2024-11-01 | 2024-11-05 | John Smith | 3 | 100 | Complete |  | Client meeting scheduled
2 | UI Design | 2024-11-06 | 2024-11-12 | Jane Doe | 5 | 75 | In Progress | 1 | Design mockups sent for review
3 | Frontend Development | 2024-11-13 | 2024-11-26 | David Lee | 10 | 50 | In Progress | 2 | API integration pending
4 | Backend Development | 2024-11-13 | 2024-11-26 | Sarah Jones | 10 | 25 | In Progress | 2 | Database schema finalized
5 | Testing | 2024-11-27 | 2024-12-03 | Team QA | 5 | 0 | Not Started | 2025-03-04 | Test plan drafted
6 | Deployment | 2024-12-04 | 2024-12-07 | John Smith | 3 | 0 | Not Started | 5 | Staging environment ready
Formulas:
Duration (Days) = NETWORKDAYS([Start Date],[End Date])